## todo
Todo tasks | Prio | Points | Order | Category | Tag | Target | Added | State | Due | Notes
Done task with number | 5 | 2 |  | demo | some_tag | CW41 | 2020-10-02 | 1
Ignored task | 3 | 1 |  | demo |  | CW41 | 2020-10-10 | -1
Open task | 2 | 2 |  | demo | some_tag | CW43 | 2020-10-12 |  |  | some note
Done task with date | 2 | 5 |  | demo |  | CW41 | 2020-10-10 | 2020-10-10 | 2020-10-13
In progress task | 2 | 5 |  | demo |  | CW42 | 2020-10-12 | 0.8
Open task | 2 | 2 |  | demo |  | CW43 | 2020-10-12 | 0
Write to-do list blog article | 1 | 3 |  | blog |  | CW42 | 2020-10-12 | 0.5 |  | https://scito.ch/content/simple-low-tech-todo-list-mangagment-libreoffice-calc-excel
Update red/yellow/green state blog article | 1 | 1 |  | blog |  | CW42 | 2020-10-10 | 2020-10-12 |  | https://scito.ch/content/redyellowgreen-state-libreoffice-calc
Note on A1: Todo task name Use a verb to describe the task
Note on B1: Priority for ordering tasks, order descending. Use number 1, 2, 3, … Use number 0 for short term high priority task. Start with the task having the lowest number.
Note on C1: Estimation in points (fibonacci numbers: 1, 2, 3, 5, 8, 13, 21) relative to other tasks
Note on E1: Category name to group tasks of the same topic
Note on F1: A tag for marking some tasks (optional feature)
Note on G1: Target date/week/event planned for working on a task. I'm using ISO calendar week numbers, CW01, CW02, … CW52. Before working on tasks, select your current target in the autofilter to focus on the tasks. So you will only see the planned task - a set of doable tasks and not all the existing tasks which might be overwhelming. After passing the target, move the tasks from the old target to a new target or remove the target for a next planning.
Note on H1: Added date Press Ctrl+; or Ctrl+. to enter the current date
Note on I1: State of the task Empty / 0: to do (red) 0 < x < 1: started (yellow) >= 1: done (green) < 0: ignored (white) Use autofilter to filter out done and ignored tasks. Press Ctrl+; or Ctrl+. to enter the current date. A date is treated as a number > 1. Avoid having many tasks in yellow state. Complete yellow tasks before starting new tasks. Or split the tasks, one that can be completed and a new smaller red task.
Note on J1: Due date of the task
Note on K1: Notes giving additional information for a task